## Projects
Project ID | Project | Finish Date | Start Date | Area | Manager | Status
1 | Fuel pump | 2023-09-22 17:00 | 2023-04-12 08:00 | Engineering | Mariem | On going
2 | Equipment installation | 2023-12-30 17:00 | 2023-06-28 08:00 | Engineering | Mondher | On going
3 | Security rules | 2023-10-11 17:00 | 2023-07-19 08:00 | Tech | Fadwa | On going
4 | Logistics Process | 2023-09-08 17:00 | 2023-02-11 08:00 | Quality | Ahmed | On going
5 | Warehouse rebuild | 2023-08-30 17:00 | 2023-03-15 08:00 | Quality | Ahmed | Finished

## Managers
Manager | Image URL
Ahmed | https://github.com/Bunisness-IT/Power-BI/blob/main/Images%26%20Templates/Mark1.jpg
Mondher | https://github.com/Bunisness-IT/Power-BI/blob/main/Images%26%20Templates/John1.jpg
Mariem | https://github.com/Bunisness-IT/Power-BI/blob/main/Images%26%20Templates/Maria1.jpg
Fadwa | https://github.com/Bunisness-IT/Power-BI/blob/main/Images%26%20Templates/Julia1.jpg

## Tasks
TaskIntUID | Actual Cost | Actual Duration | Actual Workload | Forecasted Cost | Forecasted Workload | Forecasted Duration | Finish | Start | EDT | Project ID | Task | Criticality | Baseline Cost | Baseline Workload | Baseline Duration
2 | 12000 | 10 | 80 | 12000 | 80 | 10 | 2023-04-23 | 2023-04-12 | 1.1 | 1 | Create the Scope Statement | Non Critical | 12000 | 80 | 10
2 | 3840 | 6 | 48 | 3840 | 48 | 6 | 2023-07-26 | 2023-07-19 | 1.1 | 3 | Create the Communication Plan | Non Critical | 3840 | 48 | 6
2 | 1920 | 2 | 16 | 1920 | 16 | 2 | 2023-06-29 | 2023-06-28 | 1.1 | 2 | Plan the Risks | Non Critical | 1920 | 16 | 2
2 | 3840 | 4 | 32 | 3840 | 32 | 4 | 2023-02-16 | 2023-02-11 | 1.1 | 4 | Plan the Schedule | Non Critical | 3840 | 32 | 4
2 | 1920 | 3 | 24 | 1920 | 24 | 3 | 2023-03-17 | 2023-03-15 | 1.1 | 5 | Consolidate the Project Plan | Non Critical | 1920 | 24 | 3
3 | 1200 | 1 | 8 | 1200 | 8 | 1 | 2023-04-26 | 2023-04-26 | 1.2 | 1 | Planning Executed | Non Critical | 1200 | 8 | 1
3 | 960 | 1 | 8 | 960 | 8 | 1 | 2023-06-30 | 2023-06-30 | 1.2 | 2 | Procure materials for the tank | Non Critical | 960 | 8 | 1
3 | 640 | 1 | 8 | 640 | 8 | 1 | 2023-07-27 | 2023-07-27 | 1.2 | 3 | Prepare the tank site and lay the foundation | Non Critical | 640 | 8 | 1
3 | 960 | 1 | 8 | 960 | 8 | 1 | 2023-02-17 | 2023-02-17 | 1.2 | 4 | Construct the tank | Non Critical | 960 | 8 | 1
3 | 640 | 1 | 8 | 640 | 8 | 1 | 2023-03-18 | 2023-03-18 | 1.2 | 5 | Coat the tank | Non Critical | 640 | 8 | 1
4 | 1280 | 2 | 16 | 1280 | 16 | 2 | 2023-07-29 | 2023-07-28 | 1.3 | 3 | Tank constructed | Non Critical | 1280 | 16 | 2
4 | 2400 | 2 | 16 | 2400 | 16 | 2 | 2023-04-28 | 2023-04-27 | 1.3 | 1 | Procure materials for the cover | Non Critical | 2400 | 16 | 2
4 | 1920 | 2 | 16 | 1920 | 16 | 2 | 2023-07-02 | 2023-07-01 | 1.3 | 2 | Install the structure | Non Critical | 1920 | 16 | 2
4 | 960 | 1 | 8 | 960 | 8 | 1 | 2023-02-18 | 2023-02-18 | 1.3 | 4 | Fabricate the cover | Non Critical | 960 | 8 | 1
4 | 1280 | 2 | 16 | 1280 | 16 | 2 | 2023-03-22 | 2023-03-19 | 1.3 | 5 | Execute the electrical installations | Non Critical | 1280 | 16 | 2
5 | 6000 | 5 | 40 | 6000 | 40 | 5 | 2023-05-05 | 2023-04-29 | 1.4 | 1 | Implement the hydraulic installations | Non Critical | 6000 | 40 | 5
5 | 2880 | 3 | 24 | 2880 | 24 | 3 | 2023-07-07 | 2023-07-05 | 1.4 | 2 | Install the shelf | Non Critical | 2880 | 24 | 3
5 | 1920 | 3 | 24 | 1920 | 24 | 3 | 2023-08-03 | 2023-07-30 | 1.4 | 3 | Structure erected | Non Critical | 1920 | 24 | 3
5 | 1920 | 2 | 16 | 1920 | 16 | 2 | 2023-02-22 | 2023-02-19 | 1.4 | 4 | Execute the pump's electrical installations | Non Critical | 1920 | 16 | 2
5 | 1920 | 3 | 24 | 1920 | 24 | 3 | 2023-03-25 | 2023-03-23 | 1.4 | 5 | Implement the pump's hydraulic installations | Non Critical | 1920 | 24 | 3
6 | 1200 | 1 | 8 | 1200 | 8 | 1 | 2023-05-06 | 2023-05-06 | 1.5 | 1 | Connect the pump to the gas tank | Non Critical | 1200 | 8 | 1
6 | 1920 | 2 | 16 | 1920 | 16 | 2 | 2023-07-09 | 2023-07-08 | 1.5 | 2 | Conduct required tests | Non Critical | 1920 | 16 | 2
6 | 2280 | 2 | 16 | 2280 | 16 | 2 | 2023-08-05 | 2023-08-04 | 1.5 | 3 | Pump installed | Non Critical | 1280 | 16 | 2
6 | 960 | 1 | 8 | 960 | 8 | 1 | 2023-02-23 | 2023-02-23 | 1.5 | 4 | Create the Scope Statement | Non Critical | 960 | 8 | 1
6 | 640 | 1 | 8 | 640 | 8 | 1 | 2023-03-26 | 2023-03-26 | 1.5 | 5 | Create the Communication Plan | Non Critical | 640 | 8 | 1
7 | 960 | 1 | 8 | 960 | 8 | 1 | 2023-07-12 | 2023-07-12 | 1.6 | 2 | Plan the Risks | Non Critical | 960 | 8 | 1
7 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-05-06 | 2023-05-06 | 1.6 | 1 | Plan the Schedule | Non Critical | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-08-05 | 2023-08-05 | 1.6 | 3 | Plan acquisitions | Non Critical | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-02-23 | 2023-02-23 | 1.6 | 4 | Consolidate the Project Plan | Non Critical | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-03-26 | 2023-03-26 | 1.6 | 5 | Planning Executed | Non Critical | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-07-12 | 2023-07-12 | 1.7 | 2 | Engage Suppliers | Non Critical | 0 | 0 | 0
9 | 27700 | 15 | 120 | 27700 | 120 | 15 | 2023-05-27 | 2023-05-07 | 2.1 | 1 | Receive proposals | Non Critical | 26200 | 120 | 15
9 | 0 | 0 | 0 | 1600 | 32 | 4 | 2023-08-11 | 2023-08-06 | 2.1 | 3 | Select suppliers | Critical | 1600 | 32 | 4
9 | 55200 | 30 | 720 | 55200 | 720 | 30 | 2023-04-06 | 2023-02-24 | 2.1 | 4 | Execute acquisitions | Non Critical | 55200 | 720 | 30
9 | 2000 | 5 | 40 | 2000 | 40 | 5 | 2023-04-02 | 2023-03-29 | 2.1 | 5 | Acquisitions completed | Non Critical | 2000 | 40 | 5
10 | 24000 | 30 | 480 | 24000 | 480 | 30 | 2023-07-08 | 2023-05-28 | 2.2 | 1 | Design the physical layout of the facilities | Non Critical | 24000 | 480 | 30
10 | 5760 | 6 | 48 | 28800 | 240 | 30 | 2023-08-23 | 2023-07-13 | 2.1 | 2 | Verify hydraulic and physical installations | Critical | 28800 | 240 | 30
10 | 0 | 0 | 0 | 8000 | 160 | 20 | 2023-09-08 | 2023-08-12 | 2.2 | 3 | Make necessary adjustments | Critical | 8000 | 160 | 20
10 | 24640 | 23 | 448 | 24640 | 448 | 23 | 2023-05-07 | 2023-04-07 | 2.2 | 4 | Receive the equipment | Non Critical | 24640 | 448 | 23
10 | 6400 | 10 | 80 | 6400 | 80 | 10 | 2023-04-16 | 2023-04-05 | 2.2 | 5 | Equipment Received | Non Critical | 6400 | 80 | 10
11 | 0 | 0 | 0 | 9600 | 80 | 10 | 2023-09-06 | 2023-08-24 | 2.2 | 2 | Distribute the equipment in the Warehouse | Critical | 9600 | 80 | 10
11 | 4800 | 6 | 96 | 24000 | 480 | 30 | 2023-08-19 | 2023-07-09 | 2.3 | 1 | Install the equipment | Critical | 24000 | 480 | 30
11 | 0 | 0 | 0 | 640 | 8 | 1 | 2023-09-09 | 2023-09-09 | 2.3 | 3 | Installations executed | Critical | 640 | 8 | 1
11 | 960 | 1 | 8 | 960 | 8 | 1 | 2023-05-10 | 2023-05-10 | 2.3 | 4 | Perform electrical tests | Non Critical | 960 | 8 | 1
11 | 800 | 1 | 16 | 800 | 16 | 1 | 2023-04-19 | 2023-04-19 | 2.3 | 5 | Perform hydraulic tests | Non Critical | 800 | 16 | 1
12 | 0 | 0 | 0 | 16000 | 320 | 20 | 2023-09-16 | 2023-08-20 | 2.4 | 1 | Verify equipment | Critical | 16000 | 320 | 20
12 | 0 | 0 | 0 | 9600 | 80 | 10 | 2023-09-20 | 2023-09-07 | 2.3 | 2 | Test equipment | Critical | 9600 | 80 | 10
12 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-09 | 2023-09-09 | 2.4 | 3 | Tests conducted | Critical | 0 | 0 | 0
12 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-05-10 | 2023-05-10 | 2.4 | 4 | Consolidate the Project Plan | Non Critical | 0 | 0 | 0
12 | 800 | 1 | 8 | 800 | 8 | 1 | 2023-04-20 | 2023-04-20 | 2.4 | 5 | Planning Executed | Non Critical | 400 | 8 | 1
13 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-16 | 2023-09-16 | 2.5 | 1 | Identify areas | Critical | 0 | 0 | 0
13 | 0 | 0 | 0 | 38400 | 320 | 40 | 2023-11-15 | 2023-09-21 | 2.4 | 2 | Conduct interviews | Critical | 38400 | 320 | 40
13 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-04-20 | 2023-04-20 | 2.5 | 5 | Present report | Non Critical | 0 | 0 | 0
14 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-11-15 | 2023-11-15 | 2.5 | 2 | Create the Scope Statement | Critical | 0 | 0 | 0
14 | 0 | 0 | 0 | 16000 | 320 | 20 | 2023-10-07 | 2023-09-10 | 3.1 | 3 | Create the Communication Plan | Critical | 16000 | 320 | 20
14 | 25025 | 26 | 455 | 25025 | 455 | 26 | 2023-06-15 | 2023-05-11 | 3.1 | 4 | Plan the Risks | Non Critical | 25025 | 455 | 26
15 | 13200 | 15 | 240 | 13200 | 240 | 15 | 2023-07-06 | 2023-06-16 | 3.2 | 4 | Plan the Schedule | Non Critical | 13200 | 240 | 15
15 | 3200 | 5 | 40 | 3200 | 40 | 5 | 2023-04-27 | 2023-04-21 | 3.1 | 5 | Areas identified | Non Critical | 3200 | 40 | 5
15 | 0 | 0 | 0 | 640 | 8 | 1 | 2023-10-08 | 2023-10-08 | 3.2 | 3 | Develop training | Critical | 640 | 8 | 1
15 | 6360 | 15 | 0 | 6360 | 0 | 15 | 2023-05-27 | 2023-05-07 | 3.1 | 1 | Obtain approval | Non Critical | 6060 | 0 | 15
16 | 800 | 2 | 16 | 800 | 16 | 2 | 2023-04-29 | 2023-04-28 | 3.2 | 5 | Execute training | Non Critical | 800 | 16 | 2
16 | 1600 | 2 | 32 | 1600 | 32 | 2 | 2023-05-31 | 2023-05-28 | 3.2 | 1 | Training Executed | Non Critical | 1600 | 32 | 2
16 | 0 | 0 | 0 | 3840 | 32 | 4 | 2023-11-19 | 2023-11-16 | 3.1 | 2 | Create the Scope Statement | Critical | 3840 | 32 | 4
16 | 0 | 0 | 0 | 800 | 16 | 1 | 2023-10-11 | 2023-10-11 | 3.3 | 3 | Create the Communication Plan | Critical | 800 | 16 | 1
16 | 960 | 1 | 8 | 960 | 8 | 1 | 2023-07-07 | 2023-07-07 | 3.3 | 4 | Plan the Risks | Non Critical | 960 | 8 | 1
17 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-07-07 | 2023-07-07 | 3.4 | 4 | Plan the Schedule | Non Critical | 0 | 0 | 0
17 | 800 | 1 | 16 | 800 | 16 | 1 | 2023-06-01 | 2023-06-01 | 3.3 | 1 | Consolidate the Project Plan | Non Critical | 800 | 16 | 1
17 | 0 | 0 | 0 | 640 | 16 | 2 | 2023-11-23 | 2023-11-22 | 3.2 | 2 | Planning Executed | Critical | 640 | 16 | 2
17 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-10-11 | 2023-10-11 | 3.4 | 3 | Gather requirements | Critical | 0 | 0 | 0
17 | 90000 | 20 | 0 | 90000 | 0 | 20 | 2023-05-27 | 2023-04-30 | 3.3 | 5 | Draw the flow | Non Critical | 80000 | 0 | 20
18 | 0 | 0 | 0 | 1280 | 32 | 4 | 2023-11-29 | 2023-11-24 | 3.3 | 2 | Obtain approval | Critical | 1280 | 32 | 4
18 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-05-27 | 2023-05-27 | 3.4 | 5 | Flow outlined | Non Critical | 0 | 0 | 0
18 | 1600 | 2 | 32 | 1600 | 32 | 2 | 2023-06-03 | 2023-06-02 | 3.4 | 1 | Obtain process details | Non Critical | 1600 | 32 | 2
19 | 3520 | 4 | 64 | 3520 | 64 | 4 | 2023-07-13 | 2023-07-08 | 4.1 | 4 | Document the processes | Non Critical | 3520 | 64 | 4
19 | 1280 | 1.6 | 25.6 | 1600 | 32 | 2 | 2023-06-07 | 2023-06-04 | 3.5 | 1 | Obtain approval | Non Critical | 1600 | 32 | 2
19 | 0 | 0 | 0 | 4800 | 40 | 5 | 2023-12-06 | 2023-11-30 | 3.4 | 2 | Processes delineated | Critical | 4800 | 40 | 5
20 | 0 | 0 | 0 | 800 | 16 | 1 | 2023-06-08 | 2023-06-08 | 3.6 | 1 | Review existing forms | Non Critical | 800 | 16 | 1
20 | 0 | 0 | 0 | 200000 | 0 | 1 | 2023-12-07 | 2023-12-07 | 3.5 | 2 | Develop new forms | Critical | 200000 | 0 | 1
20 | 5280 | 6 | 96 | 5280 | 96 | 6 | 2023-07-21 | 2023-07-14 | 4.2 | 4 | Present the forms | Non Critical | 5280 | 96 | 6
20 | 24000 | 15 | 120 | 24000 | 120 | 15 | 2023-06-17 | 2023-05-28 | 4.1 | 5 | Obtain approval | Non Critical | 24000 | 120 | 15
21 | 0 | 0 | 0 | 2560 | 64 | 4 | 2023-12-13 | 2023-12-08 | 3.6 | 2 | Forms created | Critical | 2560 | 64 | 4
21 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-06-08 | 2023-06-08 | 3.7 | 1 | Develop training | Non Critical | 0 | 0 | 0
21 | 960 | 1 | 8 | 960 | 8 | 1 | 2023-07-22 | 2023-07-22 | 4.3 | 4 | Obtain approval | Non Critical | 960 | 8 | 1
21 | 8000 | 5 | 40 | 8000 | 40 | 5 | 2023-06-24 | 2023-06-18 | 4.2 | 5 | Execute training | Non Critical | 8000 | 40 | 5
22 | 960 | 1 | 8 | 960 | 8 | 1 | 2023-07-23 | 2023-07-23 | 4.4 | 4 | Training Executed | Non Critical | 960 | 8 | 1
22 | 0 | 0 | 0 | 3200 | 80 | 5 | 2023-12-20 | 2023-12-14 | 3.7 | 2 | Create the Scope Statement | Critical | 3200 | 80 | 5
22 | 8000 | 5 | 40 | 8000 | 40 | 5 | 2023-07-01 | 2023-06-25 | 4.3 | 5 | Create the Communication Plan | Non Critical | 8000 | 40 | 5
23 | 32000 | 20 | 160 | 32000 | 160 | 20 | 2023-07-29 | 2023-07-02 | 4.4 | 5 | Plan the Risks | Non Critical | 32000 | 160 | 20
23 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-12-20 | 2023-12-20 | 3.8 | 2 | Plan the Schedule | Critical | 0 | 0 | 0
23 | 0 | 0 | 0 | 2485 | 8 | 1 | 2023-09-17 | 2023-09-17 | 4.1 | 1 | Consolidate the Project Plan | Critical | 2485 | 8 | 1
23 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-07-23 | 2023-07-23 | 4.5 | 4 | Planning Executed | Non Critical | 0 | 0 | 0
24 | 0 | 0 | 0 | 400 | 8 | 1 | 2023-09-20 | 2023-09-20 | 4.2 | 1 | Detail requirements | Critical | 400 | 8 | 1
24 | 16000 | 10 | 80 | 16000 | 80 | 10 | 2023-08-12 | 2023-07-30 | 4.5 | 5 | Obtain proposals | Non Critical | 16000 | 80 | 10
25 | 23920 | 13 | 312 | 55200 | 720 | 30 | 2023-09-03 | 2023-07-26 | 5.1 | 4 | Select the builder | Critical | 55200 | 720 | 30
25 | 0 | 0 | 0 | 400 | 8 | 1 | 2023-09-21 | 2023-09-21 | 4.3 | 1 | Contract builder | Critical | 400 | 8 | 1
25 | 0 | 0 | 0 | 640 | 16 | 2 | 2023-12-22 | 2023-12-21 | 4.1 | 2 | Builder contracted | Critical | 640 | 16 | 2
25 | 19200 | 12 | 96 | 19200 | 96 | 12 | 2023-08-30 | 2023-08-13 | 4.6 | 5 | Research suppliers | Non Critical | 19200 | 96 | 12
26 | 0 | 0 | 0 | 640 | 16 | 2 | 2023-12-24 | 2023-12-23 | 4.2 | 2 | Analyze prices | Critical | 640 | 16 | 2
26 | 0 | 0 | 0 | 1200 | 8 | 1 | 2023-09-22 | 2023-09-22 | 4.4 | 1 | Procure materials | Critical | 1200 | 8 | 1
26 | 0 | 0 | 0 | 960 | 8 | 1 | 2023-09-06 | 2023-09-06 | 5.2 | 4 | Materials acquired | Critical | 960 | 8 | 1
26 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-08-30 | 2023-08-30 | 4.7 | 5 | Execute masonry work | Non Critical | 0 | 0 | 0
27 | 0 | 0 | 0 | 1280 | 32 | 2 | 2023-12-28 | 2023-12-27 | 4.3 | 2 | Review electrical components | Critical | 1280 | 32 | 2
27 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-22 | 2023-09-22 | 4.5 | 1 | Review hydraulic components | Critical | 0 | 0 | 0
27 | 0 | 0 | 0 | 1920 | 16 | 2 | 2023-09-08 | 2023-09-07 | 5.3 | 4 | Paint walls | Critical | 1920 | 16 | 2
28 | 0 | 0 | 0 | 3200 | 48 | 2 | 2023-12-30 | 2023-12-29 | 4.4 | 2 | Install the floor | Critical | 3200 | 48 | 2
28 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-09-08 | 2023-09-08 | 5.4 | 4 | Refurbish the roof | Critical | 0 | 0 | 0
29 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-12-30 | 2023-12-30 | 4.5 | 2 | Construction completed | Critical | 0 | 0 | 0